Original: English

Revised roadmap for the ICCAT MSE processes adopted by the Commission in 2024

and revised by the SCRS in 2025

This schedule is intended to guide the development of harvest strategies for priority stocks identified in Recommendation by ICCAT on the development of Harvest Control Rules and of Management Strategy Evaluation (Rec. 15-07). It builds on the initial roadmap that was appended to the 2016 Annual Meeting report, which has been revised regularly based on the SCRS advice and Commission decisions. It provides an aspirational timeline that is subject to revision and should be considered in conjunction with the stock assessment schedule that is revised annually by the SCRS. Due to the amount of cross-disciplinary dialogue that may be needed, intersessional Panel meetings and/or meetings of the Standing Working Group on Dialogue between Fisheries Scientists and Managers (SWGSM) will be necessary. However, the exact timeline for delivery is contingent on funding, prioritization, and other work of the Commission and SCRS. Tasks are divided into four categories: Commission intersessionally, SCRS development, SCRS implementation, and Commission at Annual Meeting. The table below contains the revisions suggested by the SCRS during its 2025 plenary meeting for Commission consideration, regarding the following MSE processes: North Atlantic albacore, Atlantic bluefin tuna, North Atlantic swordfish, multi-stock tropical tunas, Western Atlantic skipjack, South Atlantic Albacore and Atlantic Blue shark. New text is underlined, and removed text is indicated with […].

|  |  | Northern Albacore | Bluefin Tuna | Northern Swordfish | Tropical Tunas (BET, YFT, Eastern SKJ) | Western Skipjack | South Atlantic Albacore | Atlantic Blue Shark |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 2025 2025 2025 | Commission intersessionally |  |  | COMM (PA4) to develop an exceptional circumstances protocol through an iterative consultation process with the SCRS that provides, inter alia, guidance on a range of appropriate management responses should exceptional circumstances be found to occur | COMM (PA1) provided guidance to the SCRS on how to handle: trade-offs in species yields; changes in effort over time; changes in gear; and, variable allocations over time. COMM (PA1) met intersessionally, with SCRS participation, to discuss CMP design and operational management objectives, considering how the multi-stock interactions are handled in the current MSE. […] […] […] | […] COMM (PA1) reviewed final MSE results. |  | Establish a small technical working group to begin considering key uncertainties for OM development. |
|  | SCRS development | SCRS to finalize the grid of reference and robustness OMs based on Stock Synthesis as part of a new MSE. SCRS to finalize the improvement of the Observation Error Model. SCRS to test the adopted MP on the new reference uncertainty grid. SCRS to test alternative candidate MPs (e.g., based on JABBA model, or empirical). | SCRS to conduct additional retuning of OMs, incorporating the CKMR estimate of western stock abundance. | SCRS to provide final advice to COMM (PA4) on criteria for determining exceptional circumstances and inclusion in the exceptional circumstances protocol to be developed by Panel 4 in consultation with the SCRS. The SCRS to continue to develop robustness scenarios, as requested by COMM. | SCRS further developed MSE framework, incorporating feedback from COMM through PA1, including developing mechanisms to implement multi-stock CMP, development of TSD, and creation of Shiny visualization tool. | SCRS finalized MSE results, incorporating feedback from COMM through PA1 including: - OM reconditioning with updated data through 2024, - CMP re-tuning […] | Secretariat compiled and shared necessary catch data for Stock Assessment by April per the workplan. SCRS established an ALB-S MSE Technical Team. |  |
|  | SCRS implementation | SCRS to evaluate existence of exceptional circumstances in accordance with the EC protocol. | SCRS to evaluate existence of exceptional circumstances in accordance with the EC protocol. SCRS to advise COMM of the TAC for 2026-2028 that results from the MP. | Should a final EC protocol be ready well in advance of the SCRS annual meeting, SCRS to evaluate existence of exceptional circumstances in accordance with that protocol. |  |  |  |  |
|  | Commission at Annual Meeting |  | COMM to continue use of the MP to set TAC on the predetermined timescale defined in the MP setting. | COMM to adopt exceptional circumstances protocol. |  | COMM to consider final evaluation of CMPs, and adopt an MP, including the TAC, at the Annual Meeting. | COMM (PA3) will be informed and provide feedback on SCRS work. | The SCRS shall inform the Commission, by 2025 on the feasibility, cost and options for developing an MSE framework. In this work, the SCRS should discuss and list the main sources of uncertainty, from the last assessment, that should be considered in the MSE. The Commission shall discuss operational management objectives, and performance indicators for CMPs. |
| 2026 and beyond* 2026 and beyond* 2026 and beyond* | Commission intersessionally | (2026) PA2 will provide guidance to SCRS on updated management objectives and performance statistics. |  |  | In 2026, COMM (PA1) to provide guidance to SCRS on CMP design. Ambassadors’ meetings to be held. | In 2026, SCRS to develop an exceptional circumstances protocol through an iterative consultation process that provides, inter alia, guidance on a range of appropriate management responses should exceptional circumstances be found to occur. | […] | (2026): SCRS to finalize the uncertainty grid and OM conditioning. Discussion and testing what variables should be in the reference grid and which should be considered as robustness tests. (2026-2029): SCRS to work on OM and CMP development. A selection of CMPs with the best performance, as per COMM management objectives, should be selected by 2029. (2027-2029): COMM (PA4) to meet intersessionally, with SCRS participation, to: - discuss CMPs, operational management objectives, and performance indicators; - refine CMPs; - recommend final operational management objectives and identify performance indicators. Ambassadors’ meetings to be held. |
|  | SCRS development | SCRS to test alternative candidate MPs (e.g., empirical, constant catch, etc.). SCRS to complete new MSE in 2026. | In 2026, SCRS to review the MP in 2027-2028 as outlined in Rec. 23-07. In 2026, SCRS to conduct status check, to begin MP review, and to present results to COMM (PA2) for feedback. In 2027, SCRS to review the MP in 2028 as outlined in Rec. 23-07. In 2027, SCRS to continue MP review, and to present results to COMM (PA2) for feedback. In 2028, SCRS to finalize MP revisions, and to present results to COMM (PA2) for final feedback. | The SCRS to review the MP on a pre-determined schedule, as defined by COMM. The first review is scheduled for 2030. | SCRS to refine MSE framework and evaluate multi-stock CMPs based on COMM (PA1) feedback. In 2027, SCRS to provide final advice to COMM (PA1) on criteria for determining ECs and inclusion in the ECP to be developed by Panel 1 in consultation with the SCRS. | In 2026, SCRS to provide final advice to COMM (PA1) on criteria for determining ECs and inclusion in the ECP to be developed by Panel 1 in consultation with the SCRS. (2027) SCRS to further develop Climate Change scenarios to test robustness of MPs. | (2026) SCRS to conduct a stock assessment using Stock Synthesis 3. (2026) SCRS to agree on: - Major sources of uncertainty to be considered in the MSE; - MSE framework structure; - Reference and robustness set of operating models; (2026) SCRS to incorporate feedback from COMM/PA3. (2027): SCRS to finalize MSE and CMP testing. (2027) SCRS to communicate final MSE results to PA3. (2028) SCRS to engage with PA3 on development of an ECP. |  |
|  | SCRS implementation | SCRS to evaluate existence of exceptional circumstances in accordance with the EC protocol. SCRS to conduct periodic assessments to ensure that the conditions considered in MP testing are still applicable to the stock. | SCRS to evaluate existence of exceptional circumstances in accordance with the EC protocol. […] In 2028, SCRS to advise COMM of the TAC for 2029-2031 based on revised MP. | SCRS to evaluate existence of exceptional circumstances in accordance with the EC protocol. SCRS to conduct periodic assessments to ensure that the conditions considered in MP testing are still applicable to the stock. The implementation schedule specifies that the first assessment is to be conducted in 2029. | (2027): SCRS to develop an exceptional circumstances protocol through an iterative consultation process that provides, inter alia, guidance on range of appropriate management responses should exceptional circumstances be found to occur. (2028): SCRS to evaluate existence of exceptional circumstances in accordance with the EC protocol. SCRS to conduct periodic assessments to ensure that the conditions considered in MP testing are still applicable to the stocks. | SCRS to evaluate the existence of exceptional circumstances in accordance with the EC protocol. SCRS to conduct periodic assessments to ensure that the conditions considered in MP testing are still applicable to the stock. The first status check and review is scheduled for 2031. | (2028 and beyond): SCRS to evaluate application of exceptional circumstances, to the extent possible. |  |
|  | Commission at Annual Meeting | COMM to continue use of the MP to set management measures on the predetermined timescale defined in the MP setting. Per Rec. 21-04, COMM to consider adoption of new MP in 2026. | COMM to continue use of the MP to set TAC on the predetermined timescale defined in the MP setting. COMM to adopt 2029-2031 TAC based on revised MP in 2028. | COMM to continue use of the MP to set TAC on the predetermined timescale for MP setting. | (2026 or 2027): COMM to adopt an MP, including the TACs. COMM to adopt exceptional circumstances protocol in 2027 as a new Annex in MP. COMM to continue use of the MP to set TACs on the predetermined timescale for MP setting. | COMM to continue use of the MP to set TAC on the predetermined timescale for MP setting. | (2026) COMM (PA3) will be informed and provide feedback on SCRS work. (2027): COMM (PA3) at an intersessional meeting to review draft MSE results and narrow down CMPs. […] (2027): COMM (PA3) to adopt MP. (2028): COMM (PA3) to adopt ECP as a new Annex in MP. | (Nov 2029): COMM to adopt an MP. (2029): SCRS and COMM to finalize the EC protocol, to be adopted from this point forward. |

* Assumes that the workplan is accomplished as described.

LIST OF ACRONYMS:

BET = Bigeye tuna

BFT = Bluefin tuna

COMM=Commission

CMP = Candidate Management Procedure

HCR = Harvest Control Rule

MP = Management Procedure

MSE = Management Strategy Evaluation

OM = Operating Model

SCRS = Standing Committee on Research and Statistics

TAC = Total Allowable Catch

TRO = Tropical tunas