## Sheet1
PLE_109/2025
SCRS proposal for a new format of the ICCAT MSE Roadmap
The SCRS approved for consideration by the Commission an alternative format to the ICCAT MSE roadmap document based on an EXCEL worksheet. The aim is to facilitate reading, comparison among processes and navigation. The Committee updated the MSE roadmap in the new format and recommended that the Commission consider replacing the current ICCAT MSE roadmap document format with the new format. However, the Committed noted that further changes may be needed to improve consistency regarding the terminology used among the different MSEs.
Stock | MP adoption (actual or planned) | ECP adoption (actual or planned) | Next year to run MP | Next stock status check | Next MP review | 2025 Progress |  | 2026 Workplan |  | 2027 Workplan |  | 2028 Workplan |  | 2029 Workplan
[6 empty] | SCRS | COMM | SCRS | COMM | SCRS | COMM | SCRS | COMM | SCRS | COMM
Northern Albacore | 2021 | 2021 | 2026 | 2029 | 2026 | Finalized OMs & estimation model. Tested current MP and alternatives specified in Rec. 21-05. Checked for ECs. |  | Present progress to PA2 at intersessional meeting. Run the current and alternative MPs to provide TAC for 2027-2029. | PA2 to meet intersessionally to provide feedback on how to finalize the MSE (objectives, performance indicators, MPs, tuning). Adopt 2027-2029 TAC at the annual meeting based on current or alternative MP. | Check for ECs. Conduct any pending analyses as requested by COM or SCRS |  | Check for ECs. Test integration of using joint juvenile index in MP |  | Benchmark assessment (status check). Run MP to provide TAC for 2030-2032. | Adopt 2030-2032 TAC at the annual meeting based on MP.
Atlantic Bluefin | 2022 | 2023 | 2025 | 2026-27 | 2027-2028 | SCRS conducted additional retuning of OMs, incorporating the CKMR estimate of western stock abundance. Checked for ECs. Provided TACs for 2026-2028. | Adopt 2026-2028 TACs based on MP. | Conduct status check. Begin MP review. Present to PA2. Check for ECs. | Review progress on status check and MP review. | Continue MP review. Present to PA2 for feedback. Check for ECs. | Review progress on MP review. | Finalize any MP revisions. Present to PA2 for final feedback. Provide TACs for 2029-2031 based on current or alternative MP. Check for ECs. | Adopt 2029-2031 TACs based on current or alternative MP. | Check for ECs.
Northern Swordfish | 2024 | 2025 | 2027 | 2029 | 2030 | Continued robustness testing, per Rec. 24-10. Developed EC criteria for ECP. Checked for ECs. | Adopt ECP at annual meeting. | Continued robustness testing, per Rec. 24-10. Check for ECs. |  | Check for ECs. Run MP to provide TAC for 2028-2030. | Adopt 2028-2030 TAC based on MP. | Check for ECs. |  | Conduct status check. Check for ECs. | Review progress on status check
Western Skipjack | 2025 | 2026 | 2028 | 2031 | 2031 | Finalized MSE, including reconditioning with data through 2024 and retuning CMPs. Developed climate change scenarios to test robustness of MPs. | PA1 to meet intersessionally to review final MSE results. Consider MP adoption at annual meeting, including the 2026-2028 TAC. | Develop EC criteria for ECP. Check for ECs. | Adopt ECP at annual meeting. | Check for ECs. |  | Check for ECs. Run the MP to provide TAC for 2029-2031. | Adopt 2029-2031 TAC based on MP. | Check for ECs.
Multi-stock Tropical tunas | 2026 | 2027 |  |  |  | Further developed MSE framework, incorporating PA1 feedback, including mechanism to implement multi-stock CMPs, development of TSD, and creation of Shiny visualization tool. | PA1 to meet intersessionally to provide guidance on how to handle: trade-offs in species yields; changes in effort over time; changes in gear use over time; and, variable allocations over time. Also to discuss CMP design and operational management objectives, considering how the multi-stock interactions are handled in the current MSE. | Refine MSE framework and evaluate multi-stock CMPs based on PA1 feedback. | PA1 to meet intersessionally to provide guidance on CMP design. Hold Ambassadors meeting. Consider MP adoption at annual meeting, including the 2027-2029 TACs. | Develop EC criteria for ECP | Adopt ECP at annual meeting (assuming 2026 MP adoption; otherwise, consider MP adoption). | Check for Ecs. |  | Check for ECs. Run MP to provide TACs for 2030-2032. | Adopt 2030-2032 TACs at the annual meeting based on MP.
Southern Albacore | 2027 | 2028 |  |  |  | Secretariat compiled and shared necessary catch data. Established ALB-S MSE Technical Team. | PA3 will be informed and provide feedback on SCRS work at the annual meeting. | Conduct stock assessment. Agree on: - Major sources of uncertainty to be considered in the MSE; - MSE framework structure; - Reference and robustness set of operating models | PA3 to provide feedback on initial MSE structure and testing. | Finalize MSE and CMP testing. | Consider MP adoption at annual meeting, including the 2028-2030 TACs. | Develop EC criteria for ECP. | Adopt ECP at annual meeting. | Check for ECs.
Atlantic Blue sharks | 2028 | 2029 |  |  |  | Conducted feasibility study. | Discuss operational management objectives and performance indicators. | Establish the Atlantic BSH MSE Technical Team; Consider the OM main uncertainties for testing in the MSE Update MSE plan and roadmap | Provide the final operational management objectives and performance indicators. | Agree on uncertainty/OMs, and develop the final OM Further develop MSE process and plans. | PA4 to meet intersessionally (if needed) to provide guidance on CMP preferences and design. | CMP development and testing Present results to PA4 | PA4 to meet intersessionally to provide guidance on final CMP preferences/shortlist | Finalize MSE and CMP testing; Develop ECP Present results to PA4. | PA4 to meet intersessionally to review final MSE results. Hold Ambassadors meeting. Consider MP adoption at annual meeting, including the TACs.