Original: English

ICCAT MSE Roadmap

In 2025 the Commission approved a new format to the ICCAT MSE Roadmap document. The aim is to facilitate reading, comparison among processes and navigation.  The table below contains the revisions suggested by the SCRS during its 2026 Plenary meeting for consideration by the Commission.

| Stock |  | MP adoption (actual or planned) |  | ECP adoption (actual or planned) |  | Next year to run MP |  | Next stock status check |  |  |  | Next MP review |  |  |  | 2026 Workplan |  |  |  |  | 2027 Workplan |  |  |  |  |  | 2028 Workplan |  |  |  |  | 2029 Workplan |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SCRS |  |  |  | COMM |  | SCRS |  |  | COMM |  | SCRS |  |  |  | COMM |  | SCRS |  |  | COMM |  |
| Northern Albacore |  | 2021/2026 |  | 2021 |  | 2026 |  | 2029 |  |  | 2032 |  |  |  | Present progress to PA2 at intersessional meeting. Run the current and alternative MPs to provide TAC for 2027-2029. |  |  |  | PA2 to meet intersessionally to provide feedback on how to finalize the MSE (objectives, performance indicators, MPs, tuning). Adopt 2027-2029 TAC at the annual meeting based on current or alternative MP. |  | Check for ECs. Conduct any pending analyses as requested by COM or SCRS. |  |  |  |  | Check for ECs. Conduct any pending analyses as requested by COM or SCRS. |  |  |  |  |  | Bench- mark assessment (status check). Run MP to provide TAC for 2030-2032. |  |  | Adopt 2030-2032 TAC at the annual meeting based on MP. |  |
| Southern Albacore |  | 2027 |  | 2028 |  |  |  |  |  |  |  |  |  |  | Conduct stock assessment Agree on: - Major sources of uncertainty to be considered in the MSE; - MSE framework structure; - Reference and robustness set of OMs. |  |  |  | PA3 to provide feedback on initial MSE structure and testing. |  | Finalize MSE and CMP testing considering the PA3 feedback. |  |  | Intersessional meetings of PA3-SCRS. Consider MP adoption at annual meeting, including the 2028-2030 TACs. |  | Develop EC criteria for ECP. |  |  |  | Adopt ECP at annual meeting. |  | Check for ECs. |  |  |  |  |
| Atlantic Bluefin |  | 2022 |  | 2023 |  | 2028 |  | To be determined, preferably for after 2028 (due to workload) |  |  | 2027-2028 |  |  |  | Conduct status check. Begin MP review. Present to PA2. Check for ECs. |  |  |  | Review progress on status check and MP review. |  | Continue MP review. Present to PA2 for feedback. Check for ECs. |  |  | Review progress on MP review. |  | Finalize any MP revisions. Present to PA2 for final feedback. Provide TACs for 2029-2031 based on current or alternative MP. Check for ECs. |  |  |  | Adopt 2029-2031 TACs based on current or alternative MP. |  | Revise ECP. Check for ECs. |  |  | Adopt new ECP. |  |
| Northern Swordfish |  | 2024 |  | 2025 |  | 2027 |  | 2029 |  |  | 2030 |  |  |  | Continued robustness testing, per Rec. 24-10. Check for ECs. |  |  |  |  |  | Continued robustness testing, per Rec. 25-10, requests from PA4. EC review. Run MP to provide TAC for 2028-2030. |  |  | Adopt 2028-2030 TAC based on MP. |  | Check for ECs. |  |  |  |  |  | Conduct status check. Check for ECs. Prepare for MSE review. |  |  | Review progress on status check. |  |
| Western Skipjack |  | 2025 |  | 2026 |  | 2028 |  | 2031 |  |  | 2031 |  |  |  | Develop EC criteria for ECP. Check for ECs. |  |  |  | Adopt ECP at annual meeting. |  | Check for ECs. |  |  |  |  | Check for ECs. Run the MP to provide TAC for 2029-2031. |  |  |  | Adopt 2029-2031 TAC based on MP. |  | Check for ECs. |  |  |  |  |
| Multi-stock Tropical tunas |  | 2028 |  | 2029 |  |  |  |  |  |  |  |  |  |  | Further develop MSE framework incorporating PA1 feedback and collaboration with Tropical Tuna SG. Build the multi-stock approach to investigate "choke" species effects and produce first round of evaluations of CMPs. SCRS to report PA1 on the status of development of the MSE and potential timeline for adoption. |  |  |  | PA1 to meet intersessionally to provide guidance on CMP design. Hold Ambassadors meeting. Consider advice from SCRS about new timeline. |  | Recondition the OM for SKJ-E Oms. Continue development of multi-stock MSE incorporating PA1 feedback. Develop communications materials for PA1 and others and seek feedback. f |  |  | PA1 to meet intersessionally to provide guidance on CMP design. Hold Ambassadors meeting. Consider MP adoption at annual meeting, including the 2029-2031 TACs. |  | Evaluate MPs for BET, YFT and E-SKJ both individually and within the multi-stock MSE framework. Develop and evaluate indicators for use within CMP. Provide and communicate advice on tradeoffs among final set of CMPs. SCRS to conduct an external technical review. |  |  |  | PA1 to meet intersessionally to provide guidance on CMP design. Hold Ambassadors meeting. Consider MP adoption at annual meeting, including the 2029-2031 TACs. |  | Develop EC criteria for ECP. Check for ECs. |  |  | Adopt ECP at annual meeting (assuming 2028 MP adoption; otherwise, consider MP adoption). |  |
| North Atlantic Blue shark |  | 2029 |  | 2030 |  |  |  |  |  |  |  |  |  |  | Establish the Atlantic BSH MSE technical team; Initiate the OM development work. Update MSE plan and roadmap. |  |  |  | Provide the final operational management objectives and performance indicators. |  | Agree on uncertainty/ OMs, and develop the final OMs. Further develop MSE process and plans. |  |  | PA4 to meet intersessionally (if needed) to provide guidance on CMP preferences and design. |  | CMP development and testing; Present results to PA4. |  |  |  | PA4 to meet intersessionally to provide guidance on final CMP preferences/shortlist. |  | Finalize MSE and CMP testing. Present results to PA4. |  |  | PA4 to meet intersessionally to review final MSE results. Hold Ambassadors meeting. Consider MP adoption at annual meeting, including the TACs. |  |
| South Atlantic Blue shark |  | 2029 |  | 2030 |  |  |  |  |  |  |  |  |  |  | Establish the Atlantic BSH MSE technical team. Update MSE plan and roadmap. |  |  |  | Provide the final operational management objectives and performance indicators. |  | Agree on uncertainty/ OMs, and develop the final OMs. Further develop MSE process and plans. |  |  | PA4 to meet intersessionally (if needed) to provide guidance on CMP preferences and design. |  | CMP development and testing. Present results to PA4. |  |  |  | PA4 to meet intersessionally to provide guidance on final CMP preferences/ shortlist. |  | Finalize MSE and CMP testing. Present results to PA4. |  |  | PA4 to meet intersessionally to review final MSE results. Hold Ambassadors meeting. Consider MP adoption at annual meeting, including the TACs. |  |